◆ CLIENT KICKOFF

Mobilize in 5 days, not 2 weeks.

The day-by-day playbook for any new agency client. From signed SOW to first deliverable out the door in one week. Every day below has one objective, one tool to run it in, and one signal that tells you the engagement is on track.

THE PROMISE Most agencies take 2–3 weeks to actually start working. This playbook compresses that to 5 business days without sacrificing rigor. By Friday, the client has a deliverable in hand and the next 90 days planned.

THE FIVE-DAY STRUCTURE

| DAY | OBJECTIVE |
| --- | --- |
| Day 1 | Intake — stakeholders mapped, access granted, scope locked, Factfinder run. |
| Day 2 | Strategy — positioning nailed, plan drafted, client sign-off by EOD. |
| Day 3 | Build — first deliverables in progress, daily update cadence established. |
| Day 4 | Review — internal QA, client preview, revisions logged. |
| Day 5 | Ship — first deliverable out, 90-day plan signed, weekly rhythm live. |

BEFORE DAY 1 SOW signed. Deposit cleared. Client seat provisioned in Agency Suite. Client Apps share link generated. Slack channel opened. Kickoff call on the calendar for Day 1 morning. If any of these are missing, Day 1 is actually Day 0 — fix them first.

Day 1  │  Intake

Goal: by end of day, you know who makes decisions on the client side, what success looks like in concrete numbers, and exactly what you're being paid to deliver. No ambiguity carries past Day 1.

MORNING — KICKOFF CALL (60 MIN)

☐  Open the call in Deal Room. Record it. Assume you will forget half of what's said.

☐  Introductions — every person on both sides. Get roles, not just names.

☐  Client walks through: business, current state, top 3 pains, what a 90-day win looks like.

☐  Agency walks through: scope from SOW, communication cadence, who does what.

☐  Confirm the single person with final sign-off authority on the client side. Name them out loud.

MIDDAY — ACCESS & STAKEHOLDERS (2 HRS)

☐  Grant client their Client Apps view. Confirm they can log in.

☐  Get credentials / access to every system you need: ad accounts, analytics, CMS, email tool.

☐  Add every stakeholder to the contact graph. Tag decision-maker, influencer, and blocker roles.

☐  Open an Inbox thread for the account. All non-formal comms go here, not email.

AFTERNOON — FACTFINDER SESSION (2 HRS)

☐  Run a Factfinder session with the decision-maker and one operator.

☐  Answer the full 40-question intake. Don't skip sections — skipped sections come back as scope creep.

☐  Save the AI-generated blueprint to Reports Drive, tagged to this client.

☐  Send blueprint to the client with a short note: "Our starting point. We'll validate this on Day 2."

DAY 1 EXIT CRITERIA Kickoff recorded. All stakeholders in the contact graph. Decision-maker identified by name. Factfinder blueprint in Drive. Next-day agenda sent by 5pm. If any of these are missing, tomorrow is behind before it starts.

Day 2  │  Strategy

Goal: the Factfinder blueprint becomes a real, sign-off-able plan. By end of day, the client has reviewed and approved the direction. Anything that can't be approved today goes into parking lot, not into the plan.

MORNING — VALIDATE THE BLUEPRINT (90 MIN)

☐  Re-read the Factfinder output with fresh eyes. Flag anything that feels off.

☐  30-min call with the decision-maker: "Here's what the blueprint says. What would you change?"

☐  Adjust the blueprint in real time. Save v2 to Drive.

MIDDAY — DRAFT THE 90-DAY PLAN (3 HRS)

Use the Agency Suite → Plan template. Every 90-day plan has four pieces:

01.  The north-star metric — one number that defines success. Not three. One.

02.  The three workstreams — the parallel tracks of work (e.g. acquisition, retention, brand).

03.  The monthly milestones — what ships end of month 1, month 2, month 3.

04.  The risks — what could derail this, what's the mitigation, who owns it.

AFTERNOON — SIGN-OFF (BY 5PM)

☐  Send the plan via Client Apps. Attach a 60-second Loom walking through it.

☐  Schedule a 20-min review call for 4pm. Short on purpose.

☐  On the call: walk through, answer questions, get explicit approval. "Are we agreed on this plan?" Wait for yes.

☐  Client signs digitally in Client Apps. Plan moves from <i>draft</i> to <i>active</i>.

THE SIGN-OFF RULE Do not start Day 3 build work without explicit Day 2 sign-off. Starting early looks like hustle. It's actually the #1 source of rework and scope fights in week two. Get the yes first.

Day 3  │  Build

Goal: the team is heads-down on the first deliverables. Client knows exactly what's happening without needing to ask. Internal tempo is established — by end of day, the first pieces are 50% done.

MORNING — KICK THE TEAM (30 MIN)

☐  Open Campaign Attack. Create workstream boards for each of the three tracks.

☐  Assign owners per deliverable. Due dates on every card. No unowned work.

☐  Standup: each owner names what they're shipping today and their one blocker.

☐  Drop any blocker into Inbox for the account manager to unblock before lunch.

MIDDAY — EXECUTE

☐  Owners execute. No client calls. No internal meetings.

☐  Account manager runs unblocking — access, approvals, clarifications.

☐  Every hour: update Campaign Attack cards with progress. Honest status, not wishful.

AFTERNOON — CLIENT UPDATE (30 MIN)

☐  Write one short update. Post in Client Apps feed.

☐  Format: "Today we did X. Tomorrow we're doing Y. Blockers: Z (or none)."

☐  No adjectives. No "incredible progress." Just facts.

☐  Attach one asset the client can see — a draft, a screenshot, a live document.

THE CLIENT UPDATE RULE Daily updates build trust faster than weekly reports. Five 100-word updates beat one 500-word status deck. Every single day. No exceptions. Even if the update is "no movement, here's why" — send it.

END OF DAY

●  Review each workstream card. Anything not 50% done? Why, and what does Day 4 look like for it?

●  If a deliverable is clearly behind — flag it in the client update tomorrow morning, not Friday afternoon.

Day 4  │  Review

Goal: deliverables at 90%, internal QA is done, client has seen a preview and given feedback. Revisions are in motion but not panic. Friday ship day stays achievable.

MORNING — INTERNAL QA (2 HRS)

☐  Each workstream owner walks peers through their work. 20 min each.

☐  Use the QA template: does it solve the stated problem? is it on-brand? is it measurable?

☐  Peer reviewer writes 3 specific pieces of feedback. No "looks good." Specific only.

☐  Owner addresses feedback before lunch. Not perfection — good-enough-to-ship.

MIDDAY — CLIENT PREVIEW (60 MIN)

☐  Schedule a 45-min preview call with decision-maker and one operator.

☐  Walk through each deliverable. Explain the <i>why</i>, not just the <i>what</i>.

☐  Do not pitch. Do not defend. Ask for specific feedback: "What should change before Friday?"

☐  Capture every piece of feedback in Deal Room as action items with owners.

AFTERNOON — REVISIONS

☐  Triage client feedback: must-fix (Friday), nice-to-have (next week), out of scope (note and schedule).

☐  Owners start revisions immediately. Don't batch to end of day — momentum matters more than polish.

☐  Account manager confirms revision scope with client in writing by 4pm.

WHAT "OUT OF SCOPE" REALLY MEANS Out of scope ≠ "no." Out of scope = "yes, and it's a new workstream we'll price separately." Capture it in Agency Suite as an opportunity, not as a complaint. Every out-of-scope ask is future revenue if you handle it well today.

END OF DAY

●  Confirm Friday ship is achievable. If not, the client hears about it tonight, not Friday morning.

●  Send a preview of tomorrow's deliverables and the weekly rhythm going forward.

Day 5  │  Ship

Goal: first deliverables are in client's hands. Weekly rhythm is defined and live. Client is in the dashboard on their own, checking progress without needing you. This is the real transition from kickoff to engagement.

MORNING — FINAL POLISH + SHIP

☐  Each owner does one final pass. Final ≠ perfect. Final = ready to use.

☐  Ship each deliverable to Client Apps. Tag the decision-maker.

☐  Write a 2-paragraph ship note per deliverable: what it is, how to use it, what's next.

MIDDAY — 90-DAY KICKOFF CALL (45 MIN)

☐  Walk the client through the delivered work. Show them where everything lives in Client Apps.

☐  Review the 90-day plan from Day 2. Confirm workstreams for month 1.

☐  Lock the weekly rhythm: one update per day, one call per week, one report per month.

☐  Decision-maker confirms: who on their side attends the weekly call, who gets the daily updates.

AFTERNOON — HANDOFF TO STEADY STATE

☐  Internal retro — what worked in the kickoff week, what to fix for the next new client.

☐  Update the Library entry for this client type if anything new came up.

☐  Set up the weekly recurring call in Campaign Cal with the agreed attendees.

☐  Move the account from "Kickoff" to "Active" in Agency Suite.

THE MONDAY AFTER By Monday of week 2, the client should already know where to look in Client Apps for progress. If they're emailing you "how's it going?" in week 2, the kickoff didn't land. Run a 15-min tour of the dashboard early that week and fix it fast.

The ongoing rhythm

THE WEEKLY MOTION

●  Mon–Fri — one update per day in Client Apps. Never skip. Even "no change, here's why."

●  Wed — 30-min sync call. Walk through what shipped, what's next, any blockers.

●  Fri — end-of-week summary in Client Apps feed. Three bullets: shipped, shipping next week, asks.

●  Month-end — one-page report in Reports Drive. Numbers against the north-star metric. No decks.

QUESTIONS? Every agency playbook update gets posted in the #agency-suite channel inside the dashboard. If something broke in your kickoff — tell us. The next version of this playbook will fix it.